## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the proces and include a detailed description of every step. Add reasoning on why you took certain descisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description
Unity Research | 1 | 2021-05-03 | When tasked with creating a maze within Unity, my first point of action was to research the current version of Unity and familiarise myself with it. This included installing the latest version and completing a tutorial for 2D games within the application. After this I was confident with the basics of creating and modifying elements within the Unity engine.
Maze research | 1 | 2021-05-03 | Before I could create anything within unity, I had to ensure I fully understood the specification set out to me. I performed research on the different ways that mazes could be generated. I was particularly interested in the recursive divide method as I am already familiar with recursive projects and believe this would be the most efficient option, however I also researched the hunt and kill method. When I reach the implementation stage of the project , I will decide which algorithm would be more suitable at that stage.
Create the UI elements for the maze | 2 | 2021-05-04 | I used this tutorial, https://www.youtube.com/watch?v=rsZM3q74Q2k, to learn how to create a user interface within Unity and designed what the user would see while the program is running. I encountered an issue with components disappearing at certain angles, I was able to resolve this issue by modifying the z-axis allowing for components to be placed on top of each other. I also set up the camera object to frame the canvas correctly on the screen.
Create the maze objects and initialise them within unity | 3 | 2021-05-05 | I started by creating the individual objects to be generated by the script during runtime. I created a floor for the maze for each cell, as well as a wall which can be translated and rotated to make the four walls in each cell. I created a C# script to create a floor and four walls for every cell set out by the height and width of the maze. Each of these elements were then scaled so that their size changes based on the height and width of the maze, so that the total size of the maze is always the same. After this I translated the maze by fixed amounts to ensure that is appears in the same position regardless of screen resolution or the size of the maze.
Design and create the algorithm to generate the maze | 5 | 2021-05-06 | I then researched how to manipulate the objects I had created in the previous stage using code. From this I concluded that the hunt and kill algorithm would be more appropriate as it is destructive, as it removes elements from a completed grid, as opposed to a recursive design which is constructive, which creates elements as it iterates. I chose this as it would be more efficient to code within my time constraints and is less memory intensive for a smaller scale project such as this. I used this tutorial to design my algorithm, https://weblog.jamisbuck.org/2011/1/24/maze-generation-hunt-and-kill-algorithm. I created my methods in a functional way to improve efficiency by reusing code, I also performed checks when destroying walls of the maze to ensure that the program did not attempt to destroy non-existing walls and cause runtime errors. To finish the algorithm I created a loop for the ‘walk’ portion of the algorithm which will run until it cannot go any further. The algorithm will then find a new starting position and the repeat until every cell has been visited.
Integrate functionality of the UI elements | 2 | 2021-05-07 | I researched how to integrate the button and sliders with my C# code using this post https://answers.unity.com/questions/942622/how-do-you-call-a-function-with-a-button-unity-5-u.html as well as the official documentation for unity version 2020.3.6f1. Next I created a method that is performed whenever the regenerate button is pressed that will reset the grid to the new size, determined by the sliders and create a new maze. The algorithm is then called, and a new generation is performed. I then created a separate script (DisplayXY) which takes the value from the sliders and updates them within the text on screen. The properties of the maze object and within the source code as well using additional methods.
Testing | 1 | 2021-05-07 | I had performed unit tests on each individual method as they were being developed, however now I progressed onto integration testing to ensure all parts were working together. I have created a bug report for the next step. After this I performed system testing by running the program in different states by allocating a normal amount of memory as well as a limited amount. The program performed as expected in all cases. This test also included running the program at different resolutions to check that the entire canvas was visible, this did not perform as expected and is detailed as U004 in the bug report.
Bug Fixing | 2 | 2021-05-08 | I have created a bug report as part of the accompanying documentation.
Documentation | 1 | 13/05/2021 | I have created a small guide documenting my work as well as instructions on how to use it.
Total amount of hours | 18